## Sheet1
2018
Task or Deliverable - WBS |  |  |  | Planned Start Date | Actual Start Date | Planned Completion Date | Actual Completion Date | Completion Percentage | Owner(s) | 2017-09-06 | 2017-09-13 | 2017-09-20 | 2017-09-27 | 2017-10-04 | 2017-10-11 | 2017-10-18 | 2017-10-25 | 2017-11-01 | 2017-11-08 | 2017-11-15 | 2017-11-22 | 2017-11-29 | 12/8/2017 11:59:59 PM BINDER DUE | 2017-01-03 | 2017-01-10 | 2017-01-17 | 2017-01-24 | 2017-01-31 | 2017-02-07 | 2017-02-14 | 2017-02-21 | 2017-02-28 | 2017-03-07 | 2017-03-14 | 2017-03-21 | 2017-03-28 | 2017-04-04 | 2017-04-11 | 2017-04-18 | 2017-04-25 | 2017-05-02 | 2017-05-09
1.0 Initiate Project
| 1.1 Identify Stakeholders |  |  | 2017-09-13 | 2017-09-13 | 2017-09-27 | 2017-09-27 | 100% | Group
1.2 Develop Project Charter
|  | 1.2.1 Define Scope |  | 2017-09-13 | 2017-09-13 | 2017-09-27 | 2017-10-11 | 100% | Group
|  | 1.2.2 Define Requirements |  | 2017-09-13 | 2017-09-13 | 2017-09-27 | 2017-10-11 | 100% | Group
|  | 1.2.3 Define Roles |  | 2017-09-13 | 2017-09-13 | 2017-09-27 | 2017-10-11 | 100% | Group
|  | 1.2.4 Identify Controls |  | 2017-09-13 | 2017-09-13 | 2017-09-27 | 2017-10-11 | 100% | Group
|  | 1.2.5 Identify Risks |  | 2017-09-13 | 2017-09-13 | 2017-09-27 | 2017-10-11 | 100% | Group
|  | 1.2.6 Finalize Charter |  | 2017-09-13 | 2017-09-13 | 2017-09-27 | 2017-10-11 | 100% | Group
|  |  | 1.2.6.1 Conduct Stakeholder Review | 2017-09-27 | 2017-09-27 | 2017-09-27 | 2017-09-27 | 100% | Group
|  |  | 1.2.6.2 Obtain Stakeholder Approval | 2017-09-27 | 2017-09-27 | 2017-09-27 | 2017-10-04 | 100% | Group
2.0 Plan Project
2.1 Develop Project Plan
|  | 2.1.1 Develop Work Breakdown Structure |  | 2017-09-28 | 2017-09-28 | 2017-10-04 | 2017-10-04 | 100% | John
|  | 2.1.2 Develop Project Timeline |  | 2017-09-28 | 2017-09-28 | 2017-10-04 | 2017-10-04 | 100% | John
|  | 2.1.3 Assign Project Responsibilities |  | 2017-09-28 | 2017-09-28 | 2017-10-04 | 2017-10-04 | 100% | Group
2.2 Develop Project Control Plan
|  | 2.2.1 Develop Communication Plan |  | 2017-09-28 | 2017-09-28 | 2017-10-04 | 2017-10-04 | 100% | Ashley, Justin
|  |  | 2.2.1.1 Finalize Team Collaboration Tool Selection | 2017-09-28 | 2017-09-28 | 2017-10-04 | 2017-10-04 | 100% | Group
|  |  | 2.2.1.2 Finalize Team Code Development and Sharing Tool Selection | 2017-09-28 | 2017-09-28 | 2017-10-04 | 2017-10-04 | 100% | Group
|  | 2.2.2 Develop Quality Control Plan |  | 2017-09-28 | 2017-09-28 | 2017-10-04 | 2017-10-04 | 100% | Ashley, Justin
|  | 2.2.3 Develop Change Management Plan |  | 2017-09-28 | 2017-09-28 | 2017-10-04 | 2017-10-04 | 100% | Ash, Justin
2.3 Finalize Project Plan
|  | 2.3.1 Finalize Project Requirements |  | 2017-10-04 | 2017-10-04 | 2017-10-25 | 2017-10-25 | 100% | Group
|  |  | 2.3.1.1 Develop Use Cases / User Stories | 2017-10-04 | 2017-10-04 | 2017-10-25 | 2017-10-25 | 100% | Ben, Dan, John
|  | 2.3.2 Finalize Technology Stack |  | 2017-10-04 | 2017-10-04 | 2017-10-25 | 2017-10-25 | 100% | Ashley
3.0 Complete Detailed Design
3.1 Define Application Structure
|  | 3.1.1 Design Wireframes |  | 2017-10-18 | 2017-10-18 | 2017-10-25 | 2017-10-25 | 100% | Ashley, Ben, Dan, Justin
|  | 3.1.2 Define Framework Flow |  | 2017-10-18 | 2017-10-18 | 2017-10-25 | 2017-10-21 | 100% | John
3.2 Design Database Architecture
|  | 3.2.1 Design Data Models |  | 2017-10-18 | 2017-10-18 | 2017-10-25 | 2017-10-24 | 100% | Ashley, Dan
3.3 Design Program Structure | bar: 2017-01-03 to 2017-01-10
|  | 3.3.1 Design MVC detailed components |  | 2017-10-18 | 2017-10-18 | 2017-01-10 |  | 25% | Justin | bar: 2017-01-03 to 2017-01-10
3.4 Identify Content
|  | 3.4.1 Define front-end standards (e.g. CSS) |  | 2017-10-18 | 2017-10-18 | 2017-10-25 | 2017-10-22 | 100% | Ben
|  | 3.4.2 Identify Images Needed |  | 2017-10-18 | 2017-10-18 | 2017-10-25 | 2017-10-28 | 100% | John
|  | 3.4.3 Identify APIs |  | 2017-10-18 | 2017-10-18 | 2017-10-25 | 2017-10-25 | 100% | Dan
| 3.5 Conduct Stakeholder Review |  |  | 2017-10-18 | 2017-10-19 | 2017-10-25 | 2017-10-25 | 100% | Ben Pitts, Justin Ucol, Ashley Reese
4.0 Build and Test the Application | bar: 2017-01-03 to 2017-04-11
4.1 Create the Database
4.1.1 Load constant/attribute values
4.2 Write the Code | bar: 2017-01-03 to 2017-04-11
|  | 4.2.1 MVP Phase 1: Login & User Profile |  |  |  | 2018-01-31
4.2.1.1 Login
4.2.1.2 Forgot Password
4.2.1.3 View & Edit User Settings/Profile
|  | 4.2.2 MVP Phase 2: Administrator Access: Create New Users & Registration |  |  |  | 2018-02-07
4.2.2.1 Create User & Assign Roles, Admin Privileges
4.2.2.2 New User Invite
4.2.2.3 New User Registration (after invite)
|  | 4.2.3 MVP Phase 3: Administrator: Add Supplies, Drugs, Procedures to System |  |  |  | 2018-02-14
4.2.2.4 Add Medical Supplies
4.2.2.5 Add Pharmaceuticals
4.2.2.6 Add Procedure Presets
|  | 4.2.4 MVP Phase 4: Physician CRUD EPAP |  |  |  | 2018-02-21
4.2.4.1 Save or Submit Plan
4.2.4.1.1 Select Procedure Type
4.2.4.1.2 Enter Patient Medical Data
4.2.4.1.3 Review & Adjust Drug/Supply Presets & Dosing
4.2.4.1.4 Add Additional Drug/Supply & Dosing
4.2.4.1.5 Remove Drug/Supply
4.2.4.1.6 Add notes to plan
4.2.4.2 Read Plan
4.2.4.2.1 Read Plan
4.2.4.2.2 Print Plan
4.2.4.2.3 Export Plan as PDF
4.2.4.3 Edit Plan
4.2.4.3.1 Edit Patient Medical Data
4.2.4.3.2 Edit Drug/Supply Presets & Dosing
4.2.4.3.3 Add Additional Drug/Supply & Dosing
4.2.4.3.4 Remove Drug/Supply
4.2.4.3.5 Edit existing notes (or add if none)
4.2.4.4 Delete Plan
4.2.4.5 See all plans (no security considerations)
4.2.4.6.1 See my saved plans
4.2.4.6.2 See my submitted plans by status
|  | 4.2.5 MVP Phase 5: Pharm/Tech Plan Basic Interactions |  |  |  | 2018-02-28
4.2.5.1 View Unassigned Plan Listing (Role-based)
4.2.5.2 View My Assigned Plans (User-based)
4.2.5.3 View Completed Plan Listing (Role-based)
4.2.5.2 Assign plan to applicable user & send push notifications
4.2.5.3 View Assigned Plan
4.2.5.4 Update plan status
|  | 4.2.6 MVP Phase 6: Advanced Plan Interactions |  |  |  | 2018-03-07
4.2.6.1 Administrator transfer active plans w/o request system
4.2.6.1.1 Transfer physician ownership & notification
4.2.6.1.2 Transfer pharmacist ownership & noticiation
4.2.6.1.1 Transfer technician ownership & notification
4.2.6.2 Administrator plan search (and view abiliity)
4.2.6.2.1 Search Archived Plans & view listing & plan
4.2.6.2.2 Search Active Plans & view listing & plan
4.2.6.3 Physician clawback submitted plan from workflow
4.2.6.4 System auto-archives plan after surgery
4.2.6.5 'View Archived Plan' listing for authorized users
4.2.6.6 Plan search capabilities in all plan listing views
|  | 4.2.7 MVP Phase 7: Day of Surgery View |  |  |  | 2018-03-14
4.2.7.1 View surgeries based on plan ownership
4.2.7.2 Sort surgeries based on status, room, and other fields (tbd)
4.2.7.3 Select surgery to view plan
|  | 4.2.8 MVP Phase 8: Request Systems |  |  |  | If time available
4.2.8.1 Plan Transfers
4.2.8.1.1 Transfer Plan (Send Request & Push Notification) --> only from individuals within a role. IE a physician can't transfer plan between technicians.
4.2.8.1.2 Transfer Plan Request Listing
4.2.8.1.2.1 View open transfer plan requests received (don’t show accepted/rejected)
4.2.8.1.2.2 View open transfer plan requests sent (don’t show accepted/rejected)
4.2.8.1.3 View plan from listing
4.2.8.1.4 Accept/reject plan transfer request (send notification)
4.2.8.2 Plan Suggestions (from Tech/Pharm to Physician)
4.2.8.2.1 Edit tech/pharm plan copy (add/remove items, change dosing, etc)
4.2.8.2.2 Send plan suggestion back to physician owner
4.2.8.2.3 View open plan suggestion requests (don't show accepted/rejected)
4.3 Test the Application
4.3.1 Test Application Flow | bar: 2017-03-21 to 2017-04-11
4.3.2 Test Application Content | bar: 2017-03-21 to 2017-04-11
4.3.3 Test Application Logic | bar: 2017-03-21 to 2017-04-11
4.3.4 Adjust Application | bar: 2017-03-21 to 2017-04-11
4.4 Conduct Stakeholder Review
5.0 Deploy Application | bar: 2017-04-04 to 2017-05-09
5.1 Prep Code for Move to Production | bar: 2017-04-04 to 2017-04-11
5.2 Move to Production | bar: 2017-04-11 to 2017-05-02
5.3 Transfer Ownership to Client | bar: 2017-05-09
5.3.1 Train Client | bar: 2017-05-02
5.3.2 Transfer electronic content to client | bar: 2017-05-09
6.0 Develop Project Communication Material
6.1 Develop User Manual | bar: 2017-04-11 to 2017-04-25
6.2 Develop MIT Program Deliverables
6.2.1 Develop Term I Project Binder
6.2.2 Develop Term II Project Binder
6.2.3 Develop Final Client Project Presentation | bar: 2017-04-25 to 2017-05-09