## Sheet1
2018
Task or Deliverable - WBS |  |  |  | Planned Start Date | Actual Start Date | Planned Completion Date | Actual Completion Date | Completion Percentage | Owner(s) | 2017-09-06 | 2017-09-13 | 2017-09-20 | 2017-09-27 | 2017-10-04 | 2017-10-11 | 2017-10-18 | 2017-10-25 | 2017-11-01 | 2017-11-08 | 2017-11-15 | 2017-11-22 | 2017-11-29 | 12/8/2017 11:59:59 PM BINDER DUE | 2017-01-03 | 2017-01-10 | 2017-01-17 | 2017-01-24 | 2017-01-31 | 2017-02-07 | 2017-02-14 | 2017-02-21 | 2017-02-28 | 2017-03-07 | 2017-03-14 | 2017-03-21 | 2017-03-28 | 2017-04-04 | 2017-04-11 | 2017-04-18 | 2017-04-25 | 2017-05-02 | 2017-05-09
1.0 Initiate Project
| 1.1 Identify Stakeholders |  |  | 2017-09-13 | 2017-09-13 | 2017-09-27 | 2017-09-27 | 100% | Group
1.2 Develop Project Charter
|  | 1.2.1 Define Scope |  | 2017-09-13 | 2017-09-13 | 2017-09-27 | 2017-10-11 | 100% | Group
|  | 1.2.2 Define Requirements |  | 2017-09-13 | 2017-09-13 | 2017-09-27 | 2017-10-11 | 100% | Group
|  | 1.2.3 Define Roles |  | 2017-09-13 | 2017-09-13 | 2017-09-27 | 2017-10-11 | 100% | Group
|  | 1.2.4 Identify Controls |  | 2017-09-13 | 2017-09-13 | 2017-09-27 | 2017-10-11 | 100% | Group
|  | 1.2.5 Identify Risks |  | 2017-09-13 | 2017-09-13 | 2017-09-27 | 2017-10-11 | 100% | Group
|  | 1.2.6 Finalize Charter |  | 2017-09-13 | 2017-09-13 | 2017-09-27 | 2017-10-11 | 100% | Group
|  |  | 1.2.6.1 Conduct Stakeholder Review | 2017-09-27 | 2017-09-27 | 2017-09-27 | 2017-09-27 | 100% | Group
|  |  | 1.2.6.2 Obtain Stakeholder Approval | 2017-09-27 | 2017-09-27 | 2017-09-27 | 2017-10-04 | 100% | Group
2.0 Plan Project
2.1 Develop Project Plan
|  | 2.1.1 Develop Work Breakdown Structure |  | 2017-09-28 | 2017-09-28 | 2017-10-04 | 2017-10-04 | 100% | John
|  | 2.1.2 Develop Project Timeline |  | 2017-09-28 | 2017-09-28 | 2017-10-04 | 2017-10-04 | 100% | John
|  | 2.1.3 Assign Project Responsibilities |  | 2017-09-28 | 2017-09-28 | 2017-10-04 | 2017-10-04 | 100% | Group
2.2 Develop Project Control Plan
|  | 2.2.1 Develop Communication Plan |  | 2017-09-28 | 2017-09-28 | 2017-10-04 | 2017-10-04 | 100% | Ashley, Justin
|  |  | 2.2.1.1 Finalize Team Collaboration Tool Selection | 2017-09-28 | 2017-09-28 | 2017-10-04 | 2017-10-04 | 100% | Group
|  |  | 2.2.1.2 Finalize Team Code Development and Sharing Tool Selection | 2017-09-28 | 2017-09-28 | 2017-10-04 | 2017-10-04 | 100% | Group
|  | 2.2.2 Develop Quality Control Plan |  | 2017-09-28 | 2017-09-28 | 2017-10-04 | 2017-10-04 | 100% | Ashley, Justin
|  | 2.2.3 Develop Change Management Plan |  | 2017-09-28 | 2017-09-28 | 2017-10-04 | 2017-10-04 | 100% | Ash, Justin
2.3 Finalize Project Plan
|  | 2.3.1 Finalize Project Requirements |  | 2017-10-04 | 2017-10-04 | 2017-10-25 | 2017-10-25 | 100% | Group
|  |  | 2.3.1.1 Develop Use Cases / User Stories | 2017-10-04 | 2017-10-04 | 2017-10-25 | 2017-10-25 | 100% | Ben, Dan, John
|  | 2.3.2 Finalize Technology Stack |  | 2017-10-04 | 2017-10-04 | 2017-10-25 | 2017-10-25 | 100% | Ashley
3.0 Complete Detailed Design
3.1 Define Application Structure
|  | 3.1.1 Design Wireframes |  | 2017-10-18 | 2017-10-18 | 2017-10-25 | 2017-10-25 | 100% | Ashley, Ben, Dan, Justin
|  | 3.1.2 Define Framework Flow |  | 2017-10-18 | 2017-10-18 | 2017-10-25 | 2017-10-21 | 100% | John
3.2 Design Database Architecture
|  | 3.2.1 Design Data Models |  | 2017-10-18 | 2017-10-18 | 2017-10-25 | 2017-10-24 | 100% | Ashley, Dan
3.3 Design Program Structure | bar: 2017-01-03 to 2017-01-10
|  | 3.3.1 Design MVC detailed components |  | 2017-10-18 | 2017-10-18 | 2017-01-10 |  | 25% | Justin | bar: 2017-01-03 to 2017-01-10
3.4 Identify Content
|  | 3.4.1 Define front-end standards (e.g. CSS) |  | 2017-10-18 | 2017-10-18 | 2017-10-25 | 2017-10-22 | 100% | Ben
|  | 3.4.2 Identify Images Needed |  | 2017-10-18 | 2017-10-18 | 2017-10-25 | 2017-10-28 | 100% | John
|  | 3.4.3 Identify APIs |  | 2017-10-18 | 2017-10-18 | 2017-10-25 | 2017-10-25 | 100% | Dan
| 3.5 Conduct Stakeholder Review |  |  | 2017-10-18 | 2017-10-19 | 2017-10-25 | 2017-10-25 | 100% | Ben Pitts, Justin Ucol, Ashley Reese
4.0 Build and Test the Application | bar: 2017-01-03 to 2017-04-11
4.1 Create the Database
4.1.1 Load constant/attribute values
4.2 Write the Code | bar: 2017-01-03 to 2017-04-11
|  | 4.2.1 MVP Phase 1: Login & User Profile |  |  |  | 2018-01-31
4.2.1.1 Login
4.2.1.2 Forgot Password
4.2.1.3 View & Edit User Settings/Profile
|  | 4.2.2 MVP Phase 2: Administrator Access: Create New Users & Registration |  |  |  | 2018-02-07
4.2.2.1 Create User & Assign Roles, Admin Privileges
4.2.2.2 New User Invite
4.2.2.3 New User Registration (after invite)
|  | 4.2.3 MVP Phase 3: Administrator: Add Supplies, Drugs, Procedures to System |  |  |  | 2018-02-14
4.2.2.4 Add Medical Supplies
4.2.2.5 Add Pharmaceuticals
4.2.2.6 Add Procedure Presets
|  | 4.2.4 MVP Phase 4: Physician CRUD EPAP |  |  |  | 2018-02-28
|  |  | 4.2.4.1 Save or Submit Plan |  |  | 2018-02-21
4.2.4.1.1 Select Procedure Type
4.2.4.1.2 Enter Patient Medical Data
4.2.4.1.3 Review & Adjust Drug/Supply Presets & Dosing
4.2.4.1.4 Add Additional Drug/Supply & Dosing
4.2.4.1.5 Remove Drug/Supply
4.2.4.1.6 Add notes to plan
|  |  | 4.2.4.2 Read Plan |  |  | 2018-02-21
4.2.4.2.1 Read Plan
4.2.4.2.2 Print Plan
4.2.4.2.3 Export Plan as PDF
|  |  | 4.2.4.3 Edit Plan |  |  | 2018-02-28
4.2.4.3.1 Edit Patient Medical Data
4.2.4.3.2 Edit Drug/Supply Presets & Dosing
4.2.4.3.3 Add Additional Drug/Supply & Dosing
4.2.4.3.4 Remove Drug/Supply
4.2.4.3.5 Edit existing notes (or add if none)
|  |  | 4.2.4.4 Delete Plan |  |  | 2018-02-28
|  |  | 4.2.4.5 See all plans (no security considerations) |  |  | 2018-02-28
4.2.4.6.1 See my saved plans
4.2.4.6.2 See my submitted plans by status
|  | 4.2.5 MVP Phase 5: Pharm/Tech Plan Basic Interactions |  |  |  | 2018-03-07
4.2.5.1 View Unassigned Plan Listing (Role-based)
4.2.5.2 View My Assigned Plans (User-based)
4.2.5.3 View Completed Plan Listing (Role-based)
4.2.5.2 Assign plan to applicable user & send push notifications
4.2.5.3 View Assigned Plan
4.2.5.4 Update plan status
|  | 4.2.6 MVP Phase 6: Advanced Plan Interactions |  |  |  | 2018-03-14
4.2.6.1 Administrator transfer active plans w/o request system
4.2.6.1.1 Transfer physician ownership & notification
4.2.6.1.2 Transfer pharmacist ownership & noticiation
4.2.6.1.1 Transfer technician ownership & notification
4.2.6.2 Administrator plan search (and view abiliity)
4.2.6.2.1 Search Archived Plans & view listing & plan
4.2.6.2.2 Search Active Plans & view listing & plan
4.2.6.3 Physician clawback submitted plan from workflow
4.2.6.4 System auto-archives plan after surgery
4.2.6.5 'View Archived Plan' listing for authorized users
4.2.6.6 Plan search capabilities in all plan listing views
|  | 4.2.7 MVP Phase 7: Day of Surgery View |  |  |  | 2018-03-21
4.2.7.1 View surgeries based on plan ownership
4.2.7.2 Sort surgeries based on status, room, and other fields (tbd)
4.2.7.3 Select surgery to view plan
|  | 4.2.8 MVP Phase 8: Request Systems |  |  |  | 2018-03-28
4.2.8.1 Plan Transfers
4.2.8.1.1 Transfer Plan (Send Request & Push Notification) --> only from individuals within a role. IE a physician can't transfer plan between technicians.
4.2.8.1.2 Transfer Plan Request Listing
4.2.8.1.2.1 View open transfer plan requests received (don’t show accepted/rejected)
4.2.8.1.2.2 View open transfer plan requests sent (don’t show accepted/rejected)
4.2.8.1.3 View plan from listing
4.2.8.1.4 Accept/reject plan transfer request (send notification)
4.2.8.2 Plan Suggestions (from Tech/Pharm to Physician)
4.2.8.2.1 Edit tech/pharm plan copy (add/remove items, change dosing, etc)
4.2.8.2.2 Send plan suggestion back to physician owner
4.2.8.2.3 View open plan suggestion requests (don't show accepted/rejected)
4.3 Test the Application
4.3.1 Test Application Flow | bar: 2017-03-21 to 2017-04-11
4.3.2 Test Application Content | bar: 2017-03-21 to 2017-04-11
4.3.3 Test Application Logic | bar: 2017-03-21 to 2017-04-11
4.3.4 Adjust Application | bar: 2017-03-21 to 2017-04-11
4.4 Conduct Stakeholder Review
5.0 Deploy Application | bar: 2017-04-04 to 2017-05-09
5.1 Prep Code for Move to Production | bar: 2017-04-04 to 2017-04-11
5.2 Move to Production | bar: 2017-04-11 to 2017-05-02
5.3 Transfer Ownership to Client | bar: 2017-05-09
5.3.1 Train Client | bar: 2017-05-02
5.3.2 Transfer electronic content to client | bar: 2017-05-09
6.0 Develop Project Communication Material
6.1 Develop User Manual | bar: 2017-04-11 to 2017-04-25
6.2 Develop MIT Program Deliverables
6.2.1 Develop Term I Project Binder
6.2.2 Develop Term II Project Binder
6.2.3 Develop Final Client Project Presentation | bar: 2017-04-25 to 2017-05-09