## Sheet1
2018
Task or Deliverable - WBS |  |  |  | Planned Start Date | Actual Start Date | Planned Completion Date | Actual Completion Date | Completion Percentage | Owner(s) | 2017-09-06 | 2017-09-13 | 2017-09-20 | 2017-09-27 | 2017-10-04 | 2017-10-11 | 2017-10-18 | 2017-10-25 | 2017-11-01 | 2017-11-08 | 2017-11-15 | 2017-11-22 | 2017-11-29 | 12/8/2017 11:59:59 PM BINDER DUE | 2017-01-03 | 2017-01-10 | 2017-01-17 | 2017-01-24 | 2017-01-31 | 2017-02-07 | 2017-02-14 | 2017-02-21 | 2017-02-28 | 2017-03-07 | 2017-03-14 | 2017-03-21 | 2017-03-28 | 2017-04-04 | 2017-04-11 | 2017-04-18 | 2017-04-25 | 2017-05-02 | 2017-05-09
1.0 Initiate Project
| 1.1 Identify Stakeholders |  |  | 2017-09-13 | 2017-09-13 | 2017-09-27 | 2017-09-27 | 100% | Group
1.2 Develop Project Charter
|  | 1.2.1 Define Scope |  | 2017-09-13 | 2017-09-13 | 2017-09-27 | 2017-10-11 | 100% | Group
|  | 1.2.2 Define Requirements |  | 2017-09-13 | 2017-09-13 | 2017-09-27 | 2017-10-11 | 100% | Group
|  | 1.2.3 Define Roles |  | 2017-09-13 | 2017-09-13 | 2017-09-27 | 2017-10-11 | 100% | Group
|  | 1.2.4 Identify Controls |  | 2017-09-13 | 2017-09-13 | 2017-09-27 | 2017-10-11 | 100% | Group
|  | 1.2.5 Identify Risks |  | 2017-09-13 | 2017-09-13 | 2017-09-27 | 2017-10-11 | 100% | Group
|  | 1.2.6 Finalize Charter |  | 2017-09-13 | 2017-09-13 | 2017-09-27 | 2017-10-11 | 100% | Group
|  |  | 1.2.6.1 Conduct Stakeholder Review | 2017-09-27 | 2017-09-27 | 2017-09-27 | 2017-09-27 | 100% | Group
|  |  | 1.2.6.2 Obtain Stakeholder Approval | 2017-09-27 | 2017-09-27 | 2017-09-27 | 2017-10-04 | 100% | Group
2.0 Plan Project
2.1 Develop Project Plan
|  | 2.1.1 Develop Work Breakdown Structure |  | 2017-09-28 | 2017-09-28 | 2017-10-04 | 2017-10-04 | 100% | John
|  | 2.1.2 Develop Project Timeline |  | 2017-09-28 | 2017-09-28 | 2017-10-04 | 2017-10-04 | 100% | John
|  | 2.1.3 Assign Project Responsibilities |  | 2017-09-28 | 2017-09-28 | 2017-10-04 | 2017-10-04 | 100% | Group
2.2 Develop Project Control Plan
|  | 2.2.1 Develop Communication Plan |  | 2017-09-28 | 2017-09-28 | 2017-10-04 | 2017-10-04 | 100% | Ashley, Justin
|  |  | 2.2.1.1 Finalize Team Collaboration Tool Selection | 2017-09-28 | 2017-09-28 | 2017-10-04 | 2017-10-04 | 100% | Group
|  |  | 2.2.1.2 Finalize Team Code Development and Sharing Tool Selection | 2017-09-28 | 2017-09-28 | 2017-10-04 | 2017-10-04 | 100% | Group
|  | 2.2.2 Develop Quality Control Plan |  | 2017-09-28 | 2017-09-28 | 2017-10-04 | 2017-10-04 | 100% | Ashley, Justin
|  | 2.2.3 Develop Change Management Plan |  | 2017-09-28 | 2017-09-28 | 2017-10-04 | 2017-10-04 | 100% | Ash, Justin
2.3 Finalize Project Plan
|  | 2.3.1 Finalize Project Requirements |  | 2017-10-04 | 2017-10-04 | 2017-10-25 | 2017-10-25 | 100% | Group
|  |  | 2.3.1.1 Develop Use Cases / User Stories | 2017-10-04 | 2017-10-04 | 2017-10-25 | 2017-10-25 | 100% | Ben, Dan, John
|  | 2.3.2 Finalize Technology Stack |  | 2017-10-04 | 2017-10-04 | 2017-10-25 | 2017-10-25 | 100% | Ashley
3.0 Complete Detailed Design
3.1 Define Application Structure
|  | 3.1.1 Design Wireframes |  | 2017-10-18 | 2017-10-18 | 2017-10-25 | 2017-10-25 | 100% | Ashley, Ben, Dan, Justin
|  | 3.1.2 Define Framework Flow |  | 2017-10-18 | 2017-10-18 | 2017-10-25 | 2017-10-21 | 100% | John
3.2 Design Database Architecture
|  | 3.2.1 Design Data Models |  | 2017-10-18 | 2017-10-18 | 2017-10-25 | 2017-10-24 | 100% | Ashley, Dan
3.3 Design Program Structure | bar: 2017-01-03 to 2017-01-10
|  | 3.3.1 Design MVC detailed components |  | 2017-10-18 | 2017-10-18 | 2017-01-10 |  | 25% | Justin | bar: 2017-01-03 to 2017-01-10
3.4 Identify Content
|  | 3.4.1 Define front-end standards (e.g. CSS) |  | 2017-10-18 | 2017-10-18 | 2017-10-25 | 2017-10-22 | 100% | Ben
|  | 3.4.2 Identify Images Needed |  | 2017-10-18 | 2017-10-18 | 2017-10-25 | 2017-10-28 | 100% | John
|  | 3.4.3 Identify APIs |  | 2017-10-18 | 2017-10-18 | 2017-10-25 | 2017-10-25 | 100% | Dan
| 3.5 Conduct Stakeholder Review |  |  | 2017-10-18 | 2017-10-19 | 2017-10-25 | 2017-10-25 | 100% | Ben Pitts, Justin Ucol, Ashley Reese
4.0 Build and Test the Application | bar: 2017-01-03 to 2017-04-11
4.1 Create the Database
4.1.1 Load constant/attribute values
4.2 Write the Code | bar: 2017-01-03 to 2017-04-11
|  | 4.2.1 Front End Development |  | 2018-01-03 |  |  |  |  | Ben Pitts, Justin Ucol, Ashley Reese
|  | 4.2.2 Back End Development |  | 2018-01-03 |  |  |  |  | Daniel Crittenden, John Peeler, Ashley Reese, Justin Ucol
|  | 4.2.3 Integration |  | TBD |  |  |  |  | Ashley Reese, John Peeler, Justin Ucol
4.3 Test the Application
4.3.1 Test Application Flow | bar: 2017-03-21 to 2017-04-11
4.3.2 Test Application Content | bar: 2017-03-21 to 2017-04-11
4.3.3 Test Application Logic | bar: 2017-03-21 to 2017-04-11
4.3.4 Adjust Application | bar: 2017-03-21 to 2017-04-11
4.4 Conduct Stakeholder Review
5.0 Deploy Application | bar: 2017-04-04 to 2017-05-09
5.1 Prep Code for Move to Production | bar: 2017-04-04 to 2017-04-11
5.2 Move to Production | bar: 2017-04-11 to 2017-05-02
5.3 Transfer Ownership to Client | bar: 2017-05-09
5.3.1 Train Client | bar: 2017-05-02
5.3.2 Transfer electronic content to client | bar: 2017-05-09
6.0 Develop Project Communication Material
6.1 Develop User Manual | bar: 2017-04-11 to 2017-04-25
6.2 Develop MIT Program Deliverables
6.2.1 Develop Term I Project Binder
6.2.2 Develop Term II Project Binder
6.2.3 Develop Final Client Project Presentation | bar: 2017-04-25 to 2017-05-09