## Sheet1
2018
Task or Deliverable - WBS |  |  |  | Planned Start Date | Actual Start Date | Planned Completion Date | Actual Completion Date | Completion Percentage | Owner(s) | 2017-09-06 | 2017-09-13 | 2017-09-20 | 2017-09-27 | 2017-10-04 | 2017-10-11 | 2017-10-18 | 2017-10-25 | 2017-11-01 | 2017-11-08 | 2017-11-15 | 2017-11-22 | 2017-11-29 | 12/8/2017 11:59:59 PM BINDER DUE | 2017-01-03 | 2017-01-10 | 2017-01-17 | 2017-01-24 | 2017-01-31 | 2017-02-07 | 2017-02-14 | 2017-02-21 | 2017-02-28 | 2017-03-07 | 2017-03-14 | 2017-03-21 | 2017-03-28 | 2017-04-04 | 2017-04-11 | 2017-04-18 | 2017-04-25 | 2017-05-02 | 2017-05-09
1.0 Initiate Project
1.1 Identify Stakeholders
1.2 Develop Project Charter
1.2.1 Define Scope
1.2.2 Define Requirements
1.2.3 Define Roles
1.2.4 Identify Controls
1.2.5 Identify Risks
1.2.6 Finalize Charter
1.2.6.1 Conduct Stakeholder Review
1.2.6.2 Obtain Stakeholder Approval
2.0 Plan Project
2.1 Develop Project Plan
2.1.1 Develop Work Breakdown Structure
2.1.2 Develop Project Timeline
2.1.3 Assign Project Responsibilities
2.2 Develop Project Control Plan
2.2.1 Develop Communication Plan
2.2.1.1 Finalize Team Collaboration Tool Selection
2.2.1.2 Finalize Team Code Development and Sharing Tool Selection
2.2.2 Develop Quality Control Plan
2.2.3 Develop Change Management Plan
2.3 Finalize Project Plan
2.3.1 Finalize Project Requirements
2.3.1.1 Develop Use Cases / User Stories
2.3.2 Finalize Technology Stack
3.0 Complete Detailed Design
3.1 Define Application Structure
3.1.1 Design Wireframes
3.1.2 Define Framework Flow
3.2 Design Database Architecture
3.2.1 Design Data Models
3.3 Design Program Structure
3.3.1 Design MVC detailed components
3.4 Identify Content
3.4.1 Define front-end standards (e.g. CSS)
3.4.2 Identify Images Needed
3.4.3 Identify APIs
3.5 Conduct Stakeholder Review
4.0 Build and Test the Application | bar: 2017-01-03 to 2017-04-11
4.1 Create the Database
4.1.1 Load constant/attribute values
4.2 Write the Code | bar: 2017-01-03 to 2017-04-11
4.2.1 <Enter detailed deliverables>
4.3 Test the Application
4.3.1 Test Application Flow | bar: 2017-03-21 to 2017-04-11
4.3.2 Test Application Content | bar: 2017-03-21 to 2017-04-11
4.3.3 Test Application Logic | bar: 2017-03-21 to 2017-04-11
4.3.4 Adjust Application | bar: 2017-03-21 to 2017-04-11
4.4 Conduct Stakeholder Review
5.0 Deploy Application | bar: 2017-04-04 to 2017-05-09
5.1 Prep Code for Move to Production | bar: 2017-04-04 to 2017-04-11
5.2 Move to Production | bar: 2017-04-11 to 2017-05-02
5.3 Transfer Ownership to Client | bar: 2017-05-09
5.3.1 Train Client | bar: 2017-05-02
5.3.2 Transfer electronic content to client | bar: 2017-05-09
6.0 Develop Project Communication Material
6.1 Develop User Manual | bar: 2017-04-11 to 2017-04-25
6.2 Develop MIT Program Deliverables
6.2.1 Develop Term I Project Binder
6.2.2 Develop Term II Project Binder
6.2.3 Develop Final Client Project Presentation | bar: 2017-04-25 to 2017-05-09